## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-swen-261-06-c Dice Spice
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As an Admin I want to add, delete, and edit items in inventory so that Customers can purchase my dice. | Given the admin want adds an item to e-store when they select Dice at the top of the screen then they can add their dice to the store. | PASS | KL 3/19/24 | Pass | ML 4/4/2024
| Given the admin wants to remove a dice they press the "X" on the dice then the dice will no longer be sold. | PASS | KL 3/19/24 | Pass | ML 4/4/2024
| Given the admin wants to edit a dice when they select the dice they want to edit through the Dice router then they can change the die's attributes (color, sides, etc) | PASS | KL 3/19/24 | Pass | ML 4/4/2024
As an Admin I need an admin account so that only I am able to add, remove, and edit items in inventory. | Given that I am an Admin When I am on the admin account Then I should not see a shopping cart. | PASS | KL 3/19/24 | Pass | ML 4/4/2024
| Given that I am an Admin When I log in to the admin account Then I expect to have the options to manage the dice of the e-store, such as adding, updating, and deleting dice attributes. | PASS | KL 3/19/24 | Pass | ML 4/4/2024
As a Buyer I want to filter my search so that I can find a dice based on color or sides. | Given a Customer is searching for dice when they are browsing products then a list of dice should appear that correspond to what the user is typing (color/sides) | PASS | LT 3/19/24 | Pass | ML 4/4/2024
| Given a Customer is browsing products when on Dashboard then they should see all dice in the store's inventory | PASS | LT 3/19/24 | Pass | ML 4/4/2024
As a Buyer I want an account so that I am able to purchase products. | Given that I have a user account when I login then I expect to be able to search and browse for products. | PASS | LT 3/19/24 | Pass | ML 4/4/2024
| Given that I have a user account when I login then I own a shopping cart and can add/delete item(s) from my shopping cart. | PASS | LT 3/19/24 | Pass | ML 4/4/2024
| Given that I have a user account when I login then I don't want to see any adminstrative properties such as being able to manipulate dice in inventory. | PASS | LT 3/19/24 | Pass | ML 4/4/2024
As a Buyer I want my shopping cart to save so that I can purchase them on a later date. | Given a customer is adding items to a shopping cart when they logout and log back in on a different time then their items should save in their cart. | PASS | LT 3/19/24 | Pass | ML 4/4/2024
As a Customer I want to add, remove, and decrement items in my shopping cart so that I can make large purchases and clear/remove items in my cart. | Given the customer wants to purchase dice when they click the die item then that die will be added to their shopping cart. | PASS | LT 3/19/24 | Pass | ML 4/4/2024
| Given the customer wants to remove an item from their cart when they view the contents of their shopping cart then they have the option to remove one or all amounts of that dice. | PASS | LT 3/19/24 | Pass | ML 4/4/2024
As a User I want the login system to enforce a strong password so that my account is more secure. | Given a user creates an account when they enter a password that doesn’t fulfill the requirements of a length greater than 8, at least one capital, at least one number, and a special character |  |  | Pass | LT 4/4/2024
As a Customer I want to add and remove items to my wishlist so that I can purchase these items at a later time. | Given a customer logs into the e-store, when the customer logs in then they have access to a wishlist. |  |  | Pass | LT 4/4/2024
| Given a customer adds an item to their wishlist when they look at their wishlist then they have the option to add to cart or remove it from their wishlist. |  |  | Pass | LT 4/4/2024
| Given a customer logs out of their account, when they log back in then they should see the same wishlist they had. |  |  | Pass | LT 4/4/2024
| Given a customer wants to purchase something from their wishlist when they are viewing their wishlist then there is a button for each dice to add it to their cart. |  |  | Pass | LT 4/4/2024
| Given a customer wants to clear their wishlist when they press "Clear Wishlist" then their wishlist will be completely empty. |  |  | Pass | LT 4/4/2024
As a Customer I want to leave a 1-5 star rating on a product so there is an accurate review of how good/bad a product is. | Given a customer wants to leave a rating when they are on the dice's link then they should have an option to leave a 1-5 star review |  |  | Pass | LT 4/4/2024
| Given a product has multiple ratings when a user is looking at the product then the average rating will be displayed to the user (customer or admin) |  |  | Pass | LT 4/4/2024
As a Customer I want to leave a written review on a product so that future customers can see how good/bad the product is. | Given a customer wants to leave a written review when they are on the dice's link they they should have an option to write a review. |  |  | Pass | LT 4/4/2024
| Given a customer wants to see reviews left by other people when they are on the dice's link then they should see reviews left by other customers. |  |  | Pass | LT 4/4/2024
As a Customer I want to save/manage my shipping address so that I can change my address if needed and have quick access to my address information when purchasing products. | Given a customer wants to change their address, when they go to their account settings then they should be able to add, edit, or delete their address. |  |  | Pass | LT 4/4/2024
| Given a customer wants to check out, when they go to the checkout page then they should be able to see their address. |  |  | Pass | LT 4/4/2024
As a Customer I want to save/manage my payment method so that I can use it later or change/remove it. | Given a customer wants to change their payment method, when they go to their account settings then they should be able to add, edit, or delete their credit card information. |  |  | Pass | LT 4/4/2024
| Given a customer wants to purchase products, when they are checking out then they should be able to see and use the payment method in their account. |  |  | Pass | LT 4/4/2024
As a Customer I want to proceed to checkout so that I can purchase the dice I want | Given a customer has put dice into their shopping cart, when they are ready to purchase these products then they can select "Proceed to checkout" and be brought to a checkout page. |  |  | Pass | LT 4/4/2024
| Given a customer is at checkout, when they have previously added a payment method and shipping address then they can use this information for their purchase. |  |  | Pass | LT 4/4/2024